## Sheet1
Objective | Category | Tasks / Deliverables | Start Date | End Date | Responsibility | Status / Notes
Objective: To complete and participate in all Foundations Month 2 activities before the respective deadlines
Build strong team collaboration | Teamwork | Get connected with your teammates via Slack/Zoom | 2025-06-03 | 2025-06-04 | You | Schedule call or send intro message
Build strong team collaboration | Teamwork | Decide on your team role (e.g., researcher, designer, presenter) | 2025-06-04 | 2025-06-05 | You | Choose based on your strengths
Master course content and learning requirements | Learning | Learn the content in Savanna modules (Weeks 6–9) | 2025-06-03 | 2025-06-28 | You | Allocate 1–2 hours daily
Master course content and learning requirements | Learning | Complete all individual Savanna activities | 2025-06-03 | 2025-06-28 | You | Track activity checklists weekly
Engage and collaborate on team deliverables | Project Collaboration | Participate in all team activities including developing wireframes or a 3D prototype | 2025-06-07 | 2025-06-21 | You / Team | Attend all group meetings
Engage and collaborate on team deliverables | Project Collaboration | Submit team prototype (wireframe or 3D design) | 2025-06-22 | 2025-06-24 | Team Lead | Finalize and submit
Meet academic evaluation requirements | Assessments | Complete Weekly Tests (Weeks 6–9) | 2025-06-07 | 2025-06-28 | You | Complete by end of each week
Meet academic evaluation requirements | Assessments | Submit Milestones 6–9 | 2025-06-07 | 2025-06-30 | You | Follow weekly Savanna prompts
Maintain personal balance and responsibilities | Personal Commitments | Plan and complete work projects, errands, family events | Weekly | Ongoing | You | Use Google Calendar for reminders
Stay organized and avoid burnout | Self-Management | Block study and focus time; review goals weekly | Weekly | Ongoing | You | Use Pomodoro or time-blocking